## Project plan
phase 1 | "CAFFE" |  |  | OCL (man-wks) | ISA (mn-wks) | Total (man-wks)
| SW Engineering |  |  |  |  | 15
|  | Linux port |  | 2 |  |  | Robert
|  | API adjustments |  | 3 |  |  | Alex/Harris/Robert
|  | CAFFE binding |  | 4 |  |  | Robert
|  | Verification |  | 4 |  |  | Alex/Harris/Robert
|  | Utilities |  | 2 |  |  | Alex/Harris/Robert
| Functionality/Optimization |  |  |  |  | 16 | Alex
3x3,5x5 convolutions (fwd)
|  |  | "direct convolution" | 2
|  |  | "winograd algorithm" | 4 | 8
|  |  | fusion with activation functions | 2
|  | Other convolution cases(fwd/bwd) |  |  |  | 4 | Robert
|  |  | concatenated MM | 4
|  | Other layers (fwd/bwd) |  | 8 |  | 8 | Harris
pooling
fully connected
normalization
softmax
activation functions
|  | Tensor ops |  | 12 |  |  | Mike's team
maps - add/multiply/exp etc
per slice reduce: sum/max etc.
slice/concatinate/reshape
| Total (in man-weeks) |  |  |  |  | 43
phase 2 | "TensorFlow"
Sw Engineering
API homogonization
TensorFlow functionality
TensorFlow binding
Verification
Functionality/Optimization
Kernel fusion
3x1, 1x3, 1x1 convolutions
3D convolution
Conolution by FFT
Convolution by sparse matrix multiply

## Convolutional timing
| kernel size | 3x3 |  |  |  |  | 5x5
peak throughput (TFLOPS) | config | 3x224x224x64 | 3x32x32x32 | 32x32x32x64 | 32x16x16x64 | 64x8x8x192 | 3x224x224x64 | 3x32x32x32 | 32x32x32x64 | 32x16x16x64 | 64x8x8x192
3.2 | old (TFLOPs) | 0.56 | 0.91 | 1.21 | 1.6 | 1.99 | 1.03 | 1.3 | 1.55 | 1.93 | 1.57
| new(TFLOPS) | 0.65 | 0.89 | 1.23 | 1.6 | 1.99 | 1.35 | 1.4 | 1.97 | 2.16 | 1.57
| increase % | 16.0714 | -2.1978 | 1.6529 | 0 | 0 | 31.068 | 7.6923 | 27.0968 | 11.9171 | 0
| % of the peak | 20.3125 | 27.8125 | 38.4375 | 50 | 62.1875 | 42.1875 | 43.75 | 61.5625 | 67.5 | 49.0625